## Basic testing multiple screens
Screen | Role | Feature | Use case
LOGIN | IND/SUP/ ADMIN | - | >>Correct Username+ Wrong Password
LOGIN | IND/SUP/ ADMIN | - | >>Wrong user+ Correct password
LOGIN | IND/SUP/ ADMIN | - | >>Wrong User + Wrong Password
LOGIN | IND/SUP/ ADMIN | - | >>Correct User+ Correct Pass
LOGIN | IND/SUP/ ADMIN | - | >>Correct Username+ Wrong Password+ correct captch
LOGIN | IND/SUP/ ADMIN | - | >>Wrong user+ Correct password+ Wrong captcha
LOGIN | IND/SUP/ ADMIN | - | >>Correct User+ Correct Pass+Wrong captcha
LOGIN | IND/SUP/ ADMIN | - | >>Correct User+ Correct Pass+Correct captcha
LOGIN | IND/SUP/ ADMIN | Notification pop up | >>Check Notifications for all the above use cases
LOGIN | IND/SUP/ ADMIN | Captcha Refresh | >>Captcha should be refresh
LOGIN | IND/SUP/ ADMIN | Login Button | >>After click on the login button the my document page should be opened
LOGIN | IND/SUP/ ADMIN | EYE BUTTON | >>Eye button function with close and open
Forget Password | IND/SUP/ ADMIN | - | >>Correct Email id>> A mail should be come on registered Email ID after click on the Send reset link and a notification popup should be shown up
Forget Password | IND/SUP/ ADMIN | - | >>Back to home button Function is working or not
Reset Password | IND/SUP/ ADMIN | - | >>After click on click here hyper link , which is sent on registered email id, Password reset screen should be open
Reset Password | IND/SUP/ ADMIN | EYE BUTTON | >>Eye button function with close and open
Reset Password | IND/SUP/ ADMIN | Reset password Button | >>After click on reset password , The password should be reset
Tabs | IND | - | >>Indexer able to see two tabs - API Uploads, My Documents
Tabs | SUP | - | >>Supervisor able to see 4 tabs - API Uploads, My Documents, QC Documents, Process flow
Tabs | ADMIN | - | >>Admin able to see tabs - API Uploads, My Documents, QC Documents,OCR Fail, API Logs, OCR failure & Process Flow, Split file detail
API Upload_ Upload Document | ADMIN | Upload file | >>Admin able to upload the file
API Upload_ Upload Document | IND | Batch List | >>Able to see all batches uploaded for the team to which the indexer belongs
API Upload_ Upload Document | SUP | Batch List | >>Batch list - Able to see all batches uploaded for the team to which the Supervisor belongs
API Upload_ Upload Document | ADMIN | API and Device Uploading | >>Upload document through of API and device
API Upload_ all batch | IND/SUP/ ADMIN | LIFO | >>All Batches Files as per LIFO
API Upload_ all batch | IND/SUP/ ADMIN | LIFO | >>Check with after refresh LIFO sequence should not be change
API Upload_ all batch | IND/SUP/ ADMIN | LIFO | >>After uploading new file, LIFO sequence should not be change
API Upload_ all batch | IND/SUP/ ADMIN | Screen column | >>Batch, Customer ID, External batch ID, Files Uploaded, OCR successfull, OCR failed, Uploaded on, OCR status should be shown
API Upload_ all batch | IND/SUP/ ADMIN | Number count | >>Total no of uploaded file count should be shown under file uploaded column
API Upload_ all batch | IND/SUP/ ADMIN | Number count | >>Total no of OCR Successfull file count should be shown under OCR Successfull column
API Upload_ all batch | IND/SUP/ ADMIN | Number count | >>Total no of OCR Failed file count should be shown under OCR Failed column
API Upload_ all batch | IND/SUP/ ADMIN | Assending and Dessanding | >> Click on Up and down arrow, user can change the order like assending or Dessanding
API Upload_ all batch | IND/SUP/ ADMIN | Search | >>User can search the file by external batch id, batch id and customer id
API Upload_ all batch | ADMIN | Delete | >>Only admin can see the delete button
API Upload_ all batch | ADMIN | Delete | >>Admin can delete the file during OCR processing
API Upload_ all batch | ADMIN | Delete | >>Admin can delete the file after process the file
API Upload_ all batch | ADMIN | Delete | >>If duing the processing if admin is delete the file then OCR processing should be stopped and The color of that batch should turn gray.
API Upload_ all batch | IND/SUP/ ADMIN | Delete Notification | >>if user hover on the delete batch then a notification should be appear "All file in this batch have been deleted"
API Upload_ all batch | IND/SUP/ ADMIN | - | >>User can able to see total all batch count
API Upload_ all batch | IND/SUP/ ADMIN | - | >>User can select row per page as 10/15/25/50
API Upload_ all batch | IND/SUP/ ADMIN | Toggle button | >>User can select the column according to his preferance through of toggle button.
API Upload_ all batch | IND/SUP/ ADMIN | Time | >>The time it will take for a batch to process is being displayed
API Upload_ Review Pending | IND/SUP/ ADMIN | FIFO | >>Rev Pending Files as per FIFO
API Upload_ Review Pending | IND/SUP/ ADMIN | FIFO | >>Check with after refresh FIFO sequence should not be change
API Upload_ Review Pending | IND/SUP/ ADMIN | FIFO | >>After uploading new file, FIFO sequence should not be change
API Upload_ Review Pending | IND/SUP/ ADMIN | Screen column | >>Batch, Customer ID, External batch ID, Files Uploaded, OCR successfull, OCR failed, Uploaded on, OCR status should be shown
API Upload_ Review Pending | IND/SUP/ ADMIN | Number count | >>Total no of uploaded file count should be shown under file uploaded column
API Upload_ Review Pending | IND/SUP/ ADMIN | Number count | >>Total no of OCR Successfull file count should be shown under OCR Successfull column
API Upload_ Review Pending | IND/SUP/ ADMIN | Number count | >>Total no of OCR Failed file count should be shown under OCR Failed column
API Upload_ Review Pending | IND/SUP/ ADMIN | Assending and Dessanding | >> Click on Up and down arrow, user can change the order like assending or Dessanding
API Upload_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search the file by external batch id, batch id and customer id
API Upload_ Review Pending | ADMIN | Delete | >>Only admin can delete the batch
API Upload_ Review Pending | IND/SUP/ ADMIN | Delete | >>Files that were deleted during processing should not appear in the "Batch Review Pending" section.
API Upload_ Review Pending | IND/SUP/ ADMIN | - | >>User can able to see total review pending batch count
API Upload_ Review Pending | IND/SUP/ ADMIN | - | >>User can select row per page as 10/15/25/50
API Upload_ Review Pending | IND/SUP/ ADMIN | Toggle button | >>User can select the column according to his preferance through of toggle button.
API Upload_ Review Pending | IND/SUP/ ADMIN | Time | >>The time it will take for a batch to process is being displayed
API Upload_ Review Completed | IND/SUP/ ADMIN | LIFO | >>Rev Completed Files as per LIFO
API Upload_ Review Completed | IND/SUP/ ADMIN | LIFO | >>Check with after refresh LIFO sequence should not be change
API Upload_ Review Completed | IND/SUP/ ADMIN | LIFO | >>After uploading new file, LIFO sequence should not be change
API Upload_ Review Completed | IND/SUP/ ADMIN | Screen column | >>Batch, Customer ID, External batch ID, Files Uploaded, OCR successfull, OCR failed, Uploaded on, OCR status should be shown
API Upload_ Review Completed | IND/SUP/ ADMIN | Number count | >>Total no of uploaded file count should be shown under file uploaded column
API Upload_ Review Completed | IND/SUP/ ADMIN | Number count | >>Total no of OCR Successfull file count should be shown under OCR Successfull column
API Upload_ Review Completed | IND/SUP/ ADMIN | Number count | >>Total no of OCR Failed file count should be shown under OCR Failed column
API Upload_ Review Completed | IND/SUP/ ADMIN | Assending and Dessanding | >> Click on Up and down arrow, user can change the order like assending or Dessanding
API Upload_ Review Completed | IND/SUP/ ADMIN | Search | >>User can search the file by external batch id, batch id and customer id
API Upload_ Review Completed | IND/SUP/ ADMIN | Delete | >>Only admin can delete the batch
API Upload_ Review Completed | IND/SUP/ ADMIN | - | >>Files that were deleted during processing should not appear in the "Batch Review Completed" section.
API Upload_ Review Completed | IND/SUP/ ADMIN | - | >>User can able to see total review completed batch count
API Upload_ Review Completed | IND/SUP/ ADMIN | - | >>User can select row per page as 10/15/25/50
API Upload_ Review Completed | IND/SUP/ ADMIN | Toggle button | >>User can select the column according to his preferance through of toggle button.
API Upload_ Review Completed | IND/SUP/ ADMIN | Time | >>The time it will take for a batch to process is being displayed
MY Document_ Review Pending | IND/SUP/ ADMIN | Auto batch filter | >>If I click on any batch from the API upload screen, the name of that batch should automatically appear in the search bar of the My Documents _Review Pending screen, and the documents should be filtered based on that batch.
MY Document_ Review Pending | IND/SUP/ ADMIN | - | >>When searching for the "Delete Batch" name in the My Documents screen, no files should be displayed.
MY Document_ Review Pending | IND/SUP/ ADMIN | Toggle button | >>User can select the column according to his preferance through of toggle button.
MY Document_ Review Pending | IND/SUP/ ADMIN | - | >>User can able to see total review PND batch count
MY Document_ Review Pending | IND/SUP/ ADMIN | - | >>User can select row per page as 10/15/25/50
MY Document_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search through of file name
MY Document_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search through of Batch ID
MY Document_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search through of External batch ID
MY Document_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search through of Customer ID
MY Document_ Review Pending | IND/SUP/ ADMIN | Search | >>User can search partial File name
MY Document_ Classification Review | IND/SUP/ ADMIN | - | >>All the files inside that batch should be visible on that screen.
MY Document_ Classification Review | IND/SUP/ ADMIN | Default page and Maximize file | >>The first page of the first file should be selected by default, and on the right-hand side of the screen, there should be a maximized view of that file.
MY Document_ Classification Review | IND/SUP/ ADMIN | Maximize file or right hand side _ZOOM IN | >> User can zoom in the document
MY Document_ Classification Review | IND/SUP/ ADMIN | Maximize file or right hand side _ZOOM OUT | >> User can zoom out the document
MY Document_ Classification Review | IND/SUP/ ADMIN | Maximize file or right hand side _Reset | >>After clicking the reset button once, the document should reset, removing any zoom in or out adjustments.
MY Document_ Classification Review | IND/SUP/ ADMIN | Maximize file | >>User can close the file view
MY Document_ Classification Review | IND/SUP/ ADMIN | Maximize file | >>User can adjust the file screen size
MY Document_ Classification Review | IND/SUP/ ADMIN | - | >>Batch name/ Total files/ Total Pages count should be shown on the top right hand side
MY Document_ Classification Review | IND/SUP/ ADMIN | - | >>Documents should be displayed according to the file within the batch, and the total number of pages in a file should also be shown above the file's box.
MY Document_ Classification Review | IND/SUP/ ADMIN | Split | >>The user can split multiple pages from anywhere>>Submit
MY Document_ Classification Review | IND/SUP/ ADMIN | Split | >>If there are three documents within a single file, the first document should be highlighted in blue, the second in orange, and the third in black.
MY Document_ Classification Review | IND/SUP/ ADMIN | Split | >>If I move any document into another file set, the moved file should be automatically displayed as a split until it is manually merged>> Submit
MY Document_ Classification Review | IND/SUP/ ADMIN | Merge | >>The user can merge multiple pages from anywhere>> Submit
NOTE: All the split combination use cases is continue in "Split combination use case" tab
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Mark as SD>> Submit
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>The "Mark as SD" option should appear directly on top of an invoice.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>After clicking on "Mark as SD," the invoice should be converted into SD.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Rotate.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>A file can be rotate on 90/180/270/360 degree>> Submit
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>Rotate option should be appeared any type of document
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >> Rotation has to be done manually, auto rotation from AI will not happen.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >> Rotated file would be downloaded as per the changes made by user.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>Rotated file will have extraction and snippet support on Extraction Screen.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>Rotated file will have extraction and snippet support on Extraction Screen.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Move page on another file>> submit
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>If there are multiple pages within a file, any page of that file can be moved to another file set in the classification screen.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >> Move page on another file option should be appeared any type of document
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Move Document on another file
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >> Move Document on another file option should be appeared any type of document
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>If a document within a file contains multiple pages, and the user wants to move the entire document to another file, they can use this option. It's important to note that all pages of that document should go into the file you are selecting.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>To move a file's page or the entire document, if the user clicks on any of these options, a pop-up should appear, allowing the user to choose the file into which they want to move the content. In this use case, ensure that all options of your files are visible in the dropdown, but the file from which you are moving the document or page should appear grayed out.
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Orient Image
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>If an image is tillted on an angle ranging from -10 to +10 the ai will orient the image
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This orient option is use only for Deorient file
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to DeOrient Image
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This option will work on only oriented images
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to Reprocess Images and user can see 4 type of strategy (A/ B/ C/ Z)
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This feature will change the resolution to detact the batter quality of the image
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to mark preceding pages as INV
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This option will show when the document is multiple pages
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>all the previous pages of the file will get converted into INV
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to mark Subsequent pages as INV
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This option will show when the document is multiple pages
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>all the next pages of the file will get converted into INV
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to mark preceding pages as SD
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This option will show when the document is multiple pages
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>all the previous pages of the file will get converted into SD
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>On right-clicking the mouse, a dropdown menu should appear with the option to mark Subsequent pages as SD
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>This option will show when the document is multiple pages
MY Document_ Classification Review | IND/SUP/ ADMIN | DropDown | >>all the next pages of the file will get converted into SD
MY Document_ Classification Review | IND/SUP/ ADMIN | Reset | >>After making any changes in the classification screen, if I click the reset button, all changes made by the user should be refreshed.
MY Document_ Classification Review | IND/SUP/ ADMIN | Submit | >>User can able to submit the file
MY Document_ Classification Review | IND/SUP/ ADMIN | Submit | >>After click on submit button , the changes should be visible which is done from Indexer on classification screen
MY Document_ Classification Review | IND/SUP/ ADMIN | Submit | >>Submit classification review without making any changes, all the flow should be going fine
MY Document_ Classification Review | IND/SUP/ ADMIN | Submit | >>Submit classification review making changes which is given in the "Split combination use case" sheet, all the flow should be going fine

## Sanity testing usecase_Prod
| Feature | 2023-12-14
Review - 100%
Indexer | Login | PASS
| Filteration on API Uploads & My Docs | PASS
| Indexer able to see two tabs - API Uploads, My Documents | PASS
| Batch list - Able to see all batches uploaded for the team to which the indexer belongs | PASS
| Batch Filter - User can filter the batches from his option | PASS
| Rev Pending Files as per FIFO, other Rev completed and All Batches should be shown as per LIFO | PASS
| Go to a batch and open a file under "Review Pending" | PASS
| View Classification review screen | PASS
| Submit classification review without making any changes | PASS
| Split/Merge files and submit classification review | PASS
| Thumbnails of PDF/Tiff/TIF/JPEG/JPG/PNG - large image different variations | ???
| Rotation has to be done manually, auto rotation from AI will not happen. | PASS
| Rotated file will have extraction and snippet support on Extraction Screen. | PASS
| In case if failure or Extraction & snippet support, user will have to fill the extraction data himself but the output will be as per point 2. (Controlled testing with Abhijeet) | PASS
| Draging, Movement of Pg's, Files, reordering on Classification Review Screen | FAIL
| Hard reset: Will come from Extraction Screen>Class Review Screen and will reset the changes made to the original AI classifcation (file uploded). 1) all files in extraction 2) few files in review completed 3) few files in all 3 headers and so on On clicking Hard Reset, all files of the batch123 (under any tab) will all move to Rev pending and come to original state. The Batch123 filter will reflect and the user will be able to see that Batch/file in Rev Pending. eg if Sup QC>Class Rev screen>Hard reset... the batch will move to Indexer Rev Pending in My Docs Screen and the user will be auto navigated there. eg: if admin del the file/doc from UI.. Hard reset will get the same back from Rev Class screen and files will move to Rev Pending | PASS
| Change document type and submit classification review | PASS
| In a Batch, multiple files, Do changes in Rev classification (split/merge/rotate/movement) in few files/with all files and submit. | PASS
| Step 1: Classification Review by NON INDEXER, Step 2: Extraction Review ONLY BY INDEXER, Step 3: Sup QC. Test use cases with role's combo for a Batch | PASS
| Make changes and reset classification | PASS
| If in a batch there are 10 files, file 1, 2,3,4 have been worked upon, and 5th File is modified via Rev Clas then only 5th file will go for OCR and the 4 files which hav been worked will remain the same (reset will not happen). Reset will not happen to File 6,7,8,9,10 also | PASS
| Once submitted, file should move to "Classification Reviewed" | PASS
| Go to a batch and open a file under "Classification Reviewed" | PASS
| Extraction screen : Editing mode, Extraction contouring check, Page 1, 2,3 navigation check | PASS
| View KV Extraction screen | PASS
| Check if OCR extracted values are correct and document type is correct | ??
| Ability to change vendor | ??
| Switch between pages in case of multi page documents | ??
| Switch between documents in case of multiple documents | PASS
| Click on "Review Classification" button and submit classification again and check whole flow as above | PASS
| Change values through contouring and manually typing in the fields, Check field for Validations | PASS
| Submit KV extraction. Make sure that the final output is matching with the editing done. | PASS
| Once submitted, file should move to "Review Completed" | PASS
| Check if a partially reviewed document has gone through classification review for the second time, the reviewed status should be reset | PASS
| Go to a batch and open a file under "Review Completed" | PASS
| File status should be "Reviewed" | PASS
| Unable to change any data on screen | PASS
| No submit button should be present | PASS
| File lock 30min, Multitab | PASS
Classification screen should open all files of the batch
| The next file which is not locked (being worked upon) in the batch should open, the docs on left side (thumbnails) should match with the middle image and KV extraction on the rt. | PASS
Vendor missing in the list if changed by Indexer and submitted. The same changed vendor should get submitted by Supervisor
Supervisor | Login | PASS
| Supervisor able to see 4 tabs - API Uploads, My Documents, QC Documents, Vendor Mgmt | PASS
| Batch list - Able to see all batches uploaded for the team to which the Supervisor belongs | PASS
| Batch Filter - User can filter the batches from his option | PASS
| QC Documents - Able to see all BATCHES assigned to him based on the review percentage mentioned in team | PASS
| Rev Pending Files as per FIFO, other Rev completed and All Batches should be shown as per LIFO | PASS
| Open a file under "Review Pending" | PASS
| View Classification review screen | PASS
| Submit classification review without making any changes | PASS
| Split/Merge files and submit classification review | PASS
| Thumbnails of PDF/Tiff/TIF/JPEG/JPG/PNG - large image different variations | PASS
| Rotation has to be done manually, auto rotation from AI will not happen. | PASS
| Rotated file will have extraction and snippet support on Extraction Screen. | PASS
| In case if failure or Extraction & snippet support, user will have to fill the extraction data himself but the output will be as per point 2. (Controlled testing with Abhijeet) | PASS
| Draging, Movement of Pg's, Files, reordering on Classification Review Screen | FAIL
| Hard reset: Will come from Extraction Screen>Class Review Screen and will reset the changes made to the original AI classifcation (file uploded). 1) all files in extraction 2) few files in review completed 3) few files in all 3 headers and so on On clicking Hard Reset, all files of the batch123 (under any tab) will all move to Rev pending and come to original state. The Batch123 filter will reflect and the user will be able to see that Batch/file in Rev Pending. eg if Sup QC>Class Rev screen>Hard reset... the batch will move to Indexer Rev Pending in My Docs Screen and the user will be auto navigated there. | PASS
| Rotate | PASS
| Move : From one file to another with the changes made | PASS
| Change document type and submit classification review | PASS
| Make changes and reset classification | PASS
| Once submitted, file should move to "Classification Reviewed" | PASS
| Open a file under "Classification Reviewed" | PASS
| View KV Extraction screen | PASS
| Check if OCR extracted values are correct and document type is correct | PASS
| Ability to change vendor | PASS
| Switch between pages in case of multi page documents | PASS
| Switch between documents in case of multiple documents | PASS
| Click on "Review Classification" button and submit classification again and check whole flow as above | PASS
| Change values through contouring and manually typing in the fields, Check field for Validations | PASS
| Submit KV extraction | PASS
| Once all the file submitted, file should move to "Review Completed" | PASS
| Check if a partially reviewed document has gone through classification review for the second time, the reviewed status should be reset | PASS
| Open a file under "Review Completed" | PASS
| File status should be "Reviewed" | PASS
| Unable to change any data on screen | PASS
| No submit button should be present | PASS
| Review completed files: Input PDF (post splitting/merging) Vs Output should be same once downloaded. | PASS
| Download file: not for client | PASS
| Vendor Management | PASS
| Upload new vendor list | PASS
| View vendor list | PASS
| Search vendor list with and without filters | PASS
| Export the vendor list | PASS
| Same flow as indexer when supervisor chooses to act as indexer | PASS
| Make sure the input/changes in Classification & Splitting and extraction data and reflection as Output (while exporting once the file is Review Completed) | PASS
| Vendor missing in the list if changed by Indexer and submitted. The same changed vendor should get submitted by Supervisor | PASS
PASS
Admin | Login | PASS
Admin able to see tabs - API Uploads, My Documents, QC Documents,OCR Fail, API Logs, Process Flow
| Batch list - Able to see all batches uploaded for the team to which the indexer belongs | PASS
| Batch Filter - User can filter the batches from his option | PASS
| Under Process flow -> should be able to see Vendor Mgmt, Vendor mgmt-Bol, API Settings, User Mgmt, Team Mgmt, Report Generation | PASS
| Upload Files | PASS
| Download files: Not for Client | PASS
| My Docs, API Upload Sup QC screen should work for Admin also as per the above pointers | PASS
| API Logs: Log of files uploaded | PASS
| Same flow as supervisor | PASS
| Batch list - Able to see all batches uploaded for the team to which the indexer belongs | PASS
| QC Documents - Able to see all BATCHES assigned to him based on the review percentage mentioned in team | PASS
| Rev Pending Files as per FIFO, other Rev completed and All Batches should be shown as per LIFO | PASS
| Open a file under "Review Pending" | PASS
| View Classification review screen | PASS
| Go to a batch and open a file under "Review Pending" | PASS
| Submit classification review without making any changes | PASS
| Split/Merge files and submit classification review | PASS
| Thumbnails of PDF/Tiff/TIF/JPEG/JPG/PNG - large image different variations | PASS
| Rotation has to be done manually, auto rotation from AI will not happen. | PASS
| Rotated file will have extraction and snippet support on Extraction Screen. | PASS
| In case if failure or Extraction & snippet support, user will have to fill the extraction data himself but the output will be as per point 2. (Controlled testing with Abhijeet) | PASS
| Draging, Movement of Pg's, Files, reordering on Classification Review Screen | PASS
| Rotate | PASS
| Change document type and submit classification review | PASS
| Make changes and reset classification | PASS
| Once submitted, file should move to "Classification Reviewed" | PASS
| Open a file under "Classification Reviewed" | PASS
| View KV Extraction screen | PASS
| Check if OCR extracted values are correct and document type is correct | PASS
| Ability to change vendor | PASS
| Switch between pages in case of multi page documents | PASS
| Switch between documents in case of multiple documents | PASS
| Click on "Review Classification" button and submit classification again and check whole flow as above | PASS
| Change values through contouring and manually typing in the fields, Check field for Validations | PASS
| Submit KV extraction | PASS
| Once submitted, file should move to "Review Completed" | PASS
| Check if a partially reviewed document has gone through classification review for the second time, the reviewed status should be reset | PASS
| Open a file under "Review Completed" | PASS
| File status should be "Reviewed" | PASS
| Unable to change any data on screen | PASS
| No submit button should be present | PASS
| Download file: Not for Client | PASS
| Vendor Management | PASS
| View vendor list | PASS
| Search vendor list with and without filters | PASS
| Make sure the input/changes in Classification & Splitting and extraction data and reflection as Output (while exporting once the file is Review Completed) | PASS
| Report Generation Screen | PASS
| OCR Failure Screen | PASS
| Multitab restriction | PASS
| Lock file functionality | PASS
| Shuffle (drag and drop) pages within a file | PASS
| Move page from one file to another | PASS
| Hard reset: Will come from Extraction Screen>Class Review Screen and will reset the changes made to the original AI classifcation (file uploded). 1) all files in extraction 2) few files in review completed 3) few files in all 3 headers and so on On clicking Hard Reset, all files of the batch123 (under any tab) will all move to Rev pending and come to original state. The Batch123 filter will reflect and the user will be able to see that Batch/file in Rev Pending. eg if Sup QC>Class Rev screen>Hard reset... the batch will move to Indexer Rev Pending in My Docs Screen and the user will be auto navigated there. | PASS
| Failure Handling : Controlled testing when AI APIs are failed on purpose (OCR, KVP, Snippet, Rotate, PDF Merger) Contact Abhijeet for further details | PASS
| Vendor missing in the list if changed by Indexer and submitted. The same changed vendor should get submitted by Supervisor | PASS
PASS
ADNIN/ SUPERVISOR/ INDEXER | Tabular Testing | PASS
| Draw the table bound:Add a table if not already present/extracted from the document | PASS
| Delete the Rows & Columns:Use control and click to delete row/column | PASS
| Extract the data:When creating a new table, it is mandatory to define at least 2 horizontal lines ( one full row) to be able to extract data - Table completion API When a table is already present/extracted, you're going to use AUTO COMPLETION API | PASS
| Contouring :Select a table cell to switch context from table to the selected cell - and call the snippet API by moving the contour and resizing it | PASS
| Delete the table spanning across multiple pages:We can delete the whole table spanning across the multiple pages | PASS
| Extracting the text from description:We can extract the desired text from the description using the contour | PASS
| Dropdown against every extracted columns:Column mapping to the local columns extracted from the table itself - filling values of a column using the metadata which present from the local columns | PASS
| Detect the table:It is a function which allows to detect the table in the document | PASS
| Full Width:To expand the extracted column view in the horizontal view | PASS
| Delete the table:This function will allow to delete the table | PASS
| Highlighted value in the dropdown :Once we select the local columns, it by default highlights the column for which values are fetched in that column from the document | PASS
| Clear the data :It will delete the fetched data in the respective column | PASS
Table always to be continuous:There should not be discontinuity between the pages of the table
Use Shift only to specific page:Pressing shift while dealing with column movement will allow the user to make this change reflect across all pages which have that particular column
Add to all the pages using add table:Adding a new table for a multipage document will ask you to select a range in which you want the table to be present
Shift column:
Autofill:Yet to be developed- While we type partial text in the extracted filed, it should autofill the predicted value/text
Split Columns:If we observe that content of 2 columns are merged in one column, using this feature, we can seperate the columns and contents
Reset:It will reset the table to the default as it was in the first place
Autofill:This will allow the user to type few text and then autofill the rest of the identified words from the contoured area
Addition of H & L in Vendor details:H denotes as Header only and L denotes both Header and Tabular to be available for the indexers to work on
After zoom every feature will be working as usual

## Combination
SN | Flow
1 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Edit table Use features Add row and column, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
2 | ----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Add table Use features Draw the table and extract the value, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
3 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Use features Deleted the extracted table and add new table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
4 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Use features Deleted the extracted table and reset table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
5 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Edit table Use features Add row and column, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
6 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Add table Use features Draw the table and extract the value, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
7 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Use features Deleted the extracted table and add new table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
8 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Use features Deleted the extracted table and reset table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen | Table
9 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Edit table Use features Add row and column, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
10 | ----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Add table Use features Draw the table and extract the value, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
11 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Use features Deleted the extracted table and add new table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
12 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change H TO L Use features Deleted the extracted table and reset table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
13 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Edit table Use features Add row and column, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
14 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Add table Use features Draw the table and extract the value, select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
15 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Use features Deleted the extracted table and add new table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
16 | -----Single page/ two page/ 5page/ tilted single page -----Classification: 1 page: INV TO SD 2 pages: SAME INV apply A and Z strategy 5 pages: 2 doc merge and 2 merged doc Separated and make 2 doc and 5 doc move into 2 pager file and rotate Tilted file: apply Orient feature ---Submitted Review screen 1pager direct submit 2pager changes below Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Use features Deleted the extracted table and reset table , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above | Table
-----2 Pages -----Classification: No changes ---Submitted Review screen Manually edit. Apply contouring, add text, delete value, select value on page 2 Table changes Vendor change L TO L Use features Deleted the extracted table on the second page , select drop-down, use auto fill, clear space, Manually edit. Apply contouring, add text, delete value, select value, clear data, use validation submit Review completed Check all the changes done on review pending screen, that is visible on the review completed screen Login supervisor Check classification>> Hard Reset>> Indexer again review the File>> and submitted>>File comes to super visor Supervisor Review Supervisor will repeat the step same is above
17 | Indexer review the file without any changes>>submit>> Supervisor Review the file with out any changes | Table
18 | Indexer review the file without any changes in classification >>submit>> Supervisor Review the file with out any changes | Table
1 | Change or modify manually or through the contouring >> click on save progress>> click on go back button>> click on same file>>submit>>check file in review completed : all the changes are showing which were changed on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
2 | Change or modify manually or through the contouring >> click on save progress>> click on go back button google>>click on my document>> click on same file>>submit>>check file in review completed : all the changes are showing which were changed on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
3 | Change or modify manually / Delete Value / Add Partial value through the contouring >> click on save progress>> click on Refresh button>> Submit>>check file in review completed : all the changes are showing which were changed on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
4 | Change or modify manually or through of contouring >> click on save progress>> click on Reclassification button>>click on go back button>>submit>>check file in review completed : all the changes is showing which is change on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
5 | Change or modify manually or through of contouring >> click on save progress>> click on go back button>> wait for 2 minute>>click on same file>>submit>>check file in review completed : all the changes is showing which is change on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
6 | Change or modify manually or through of contouring >> wait for 6 minute (Until all the information is automatically saved)>>submit>>check file in review completed : all the changes is showing which is change on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
7 | Change or modify manually or through of contouring >>click on save progress >>submit>>check file in review completed : all the changes is showing which is change on review pending screen and save progress | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
8 | Change or modify manually or through of contouring in 3 field >>click on save progress >>Go back>>come back on the same file>> change 2 and 3 feilds more>>submit>>check file in review completed on Indexer screen>> login Supervisor>>Click on the same batch>>submit classification without any changes>>The indexer changes should be shown to the supervisor | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
9 | 3 file in batch (1 pager, 2 pager, 3 pager)>> Change or modify with manually or through of contouring in 1 Pager file >>click on save progress >>Go back>>come back on the same file>>submit>>check file in review completed on Indexer screen>> login Supervisor>>Click on the same batch>>Change in 2 pager file on the classification screen>>Submit>>All the information will be refresh which is done by Indexer | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
10 | 3 file in batch (1 pager, 2 pager, 3 pager)>>Change or modify with manually or through of contouring in 3 field >>click on save progress >>Go back>>come back on the same file>> change 2 and 3 feilds more>>submit>>check file in review completed on Indexer screen>> login Supervisor>>Click on the same batch>>Change in 2 pager file on the classification screen>>Submit>>All the information will be refresh which is done by Indexer | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
11 | 3 file in batch (1 pager, 2 pager, 3 pager)>>Change or modify with manually or through of contouring in 1 Pager file >>Click on save progress>> Go back>>Cick on 2 pager file>> Click on reclassification button>>Split 2 pager file>>Submit>>check 1 pager file>> Indexer changes should be appered after reprocessing | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
12 | IND1 change in 2 feild >> save progress>>IND2 work on the same file and modify 2 more feilds>> Submit>>Super log and classified without any changes>> Both IND changes should be shown to supervisor QC on document review screen | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
13 | SUP1 change in 2 feild >> save progress>>SUP2 work on the same file and modify 2 more feilds>> Submit>> Both SUPERVISOR changes should be shown to Review completed screen | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
14 | SUP1 change in 2 feild >> save progress>>Ind work on the same file and modify 2 more feilds>> submit>>Super log and classified without any changes>> Both IND and supervisor changes should be shown to supervisor on QC document review screen | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
15 | indxer made some changes in 2 pager file of 1st page and save that doc and then after admin come and he made changes on 2page of doc and save that document and click on "Go back" then after indexer able to see all modified fileds. | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
16 | admin made any changes on doc and save, supervisor and indexer are able to see all those changes | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
17 | superviosr makes any changs and save, it should be visiblle to admin and indxer also | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
18 | If someone clicks on the hard reset button on the page, then all the old values should be displayed | Save Progress | PASS | fULL FLOW ind AND sUPERVISOR
| Note: This testing has been done on single pages and multiple pages also. After manually correcting and saving the information on Second page, the information is visible on the review completed screen. Note: this testing is done with Indexer and Supervisor QC screen all the use cases is working fine on the scaler Note: after review the file from supervisor side, we have checked the report validation also. all the final changes has been shown under the report in all the use cases. | Save Progress
1 | Vendor ID (Extracted from vendor list) ¦ AlphaNumeric | Based on vendor list
2 | Vendor Name ¦ AlphaNumeric | Based on vendor list
3 | Vendor Address ¦ AlphaNumeric | Based on vendor list
4 | Purchase Order Number ¦AlphaNumeric >> submit with special character | Validation
5 | Job Number ¦ AlphaNumeric >> submit with special character | Validation
6 | Invoice Number ¦ AlphaNumeric >> submit with special character | Validation
7 | Invoice Date ¦ MM/DD/YYYY | Validation
8 | Invoice Sub Total ¦ Numeric >> submit with special character >> Validation error notification | Validation
9 | Total Tax Amount ¦ Numeric >> submit with special character >> Validation error notification | Validation
10 | Invoice Freight ¦ Numeric >> submit with special character | Validation
11 | Total Invoice Amount ¦ Numeric>> submit with special character >> Validation error notification | Validation
12 | Account Number ¦ AlphaNumeric >> submit with special character | Validation
13 | Purchase Order Date ¦ MM/DD/YYYY | Validation
14 | Loan Number ¦AlphaNumeric >> submit with special character | Validation
15 | Sub Contract Number¦ AlphaNumeric >> submit with special character | Validation
16 | Vendor Registration Number ¦ AlphaNumeric>> submit with special character | Validation
17 | Pament Term¦ alphanumeric >> submit with special character | Validation
18 | Cutomer ID ¦ alphanumeric >> submit with special character | Validation

## BUG LIST
SR | BUG LIST | ZOHO ID
1 | Send "workflow" key in pages API for normal uploads | VI1-T1596
2 | total invoices = to be renamed in training docs, it should be total documents | VI1-T1597
3 | doc type should be displayed somewhere, coz now its no more just invoice custom, it can be anything, so we need to be sure AI has identified it correctly | VI1-T1598
4 | vendor details to be removed for docs other than invoices | VI1-T1599
5 | total pages in batches : undefined | VI1-T1600
6 | customer id/external batch id makes any sense in training batches, we can remove those columns all together | VI1-T1601
7 | date is not allowing the manual select | VI1-T1602
8 | directly taking the invoice flow, rather considering it as designed flow | VI1-T1603
9 | updated the doc type to jio bills and submitted, but it straightaway went to extraction and again there its showing invoice custom | VI1-T1604
10 | Date is not allowed to enter manually | VI1-T1605
11
12 | Hard Reset not working | VI1-T1606
13 | Training batches is routing to API upload | VI1-T1607
14
15 | Shuffling of key fields order during the extraction | VI1-T1608
16 | Send workflow name in training batch list and training doc list | VI1-T1609
17 | page_type in聽https://requordit-staging2.amygbserver.in/api/v2/trainingPages API coming as "Invoices Custom" even when the docType outside is jiobills | VI1-T1610
18 | Add Default keys in failure case | VI1-T1611
19 | Send workflow details even in normal review - getAllPages API | VI1-T1612
20 | -Add date format in document configuration | VI1-T1613
21 | Frontend integration | VI1-T1614
22 | Backend API update | VI1-T1615
23 | AI | VI1-T1616
24 | Accept a minimum of three keys in document configuration ( at least one mandatory) and check for duplicates | VI1-T1617
25 | Re-classification for multiple doc types | VI1-T1618
26 | s3_path_ocr_stitched_json is missing in GET document detail API | VI1-T1619
27 | add a filter for workflow listing api | VI1-T1620
28 | In training batch, Instead of "Review pending or review complete," it should be "Training PND or training completed." | VI1-T1621
29 | If an entry exists in the workflow configuration, it should not be deleted from the document configuration. | VI1-T1622
30 | Once the workflow is added by the user, it should be visible under training data and not under API upload. Once the training is done by the user, post that the same should be under API uploads. | VI1-T1623
31 | Locking feature is not working in training batch | VI1-T1624
32 | UI issue | VI1-T1625
33 | After adding a workflow, the landing page is deault page | VI1-T1626
34 | Edit option in workflow configuration is not working. And the same is not reflecting in workflow while uploading. | VI1-T1627
35 | User deleting a workflow and post that adding the same workflow with same name, getting an error saying the workflow already exists. | VI1-T1628
36 | If the workflow is not activated, still the same is visible in training upload workflow list | VI1-T1629
37 | After uploading and refreshing the training batch, the file is visible. | VI1-T1630
38 | If we disable some buttons on the "All Batches" page using the toggle button, those buttons will also be disabled on all three pages | VI1-T1631
39 | Quick Export" button is not working. | VI1-T1632
40 | If you upload samples in workflow "PO", AI is catching聽the document as "Invoice Custom" | VI1-T1633
41 | Keys and values are not visible after reclassification | VI1-T1634
42 | After the first step of classification, The keys and values are not visible for the PO | VI1-T1635
43 | Feedback mechanism is not working | VI1-T1636
44 | Need to Refresh to check the actual progress status | VI1-T1637
45 | Issue in preview of the file in review classification | VI1-T1638
46 | When the user clicks on the date box, the date disappears, but the contouring deletion is displayed. | VI1-T1639
47 | column define during the workflow creation is not visible | VI1-T1640
48 | In the process of manually inputting something into the "value" field of key extraction, some options are visible in the dropdown menu. | VI1-T1641
49 | After selecting the workflow, the "uploading box" appears for a few seconds. | VI1-T1642
50 | The validation of workflow configuration is not working | VI1-T1643
51 | Total document count is wrong in training review data | VI1-T1644
52 | Total file reviewed count is not showing | VI1-T1645
53 | Option to select the year in KnV is not present for the values with date | VI1-T1646
54 | Same keys are getting created in work configration if one entered key is in CAPS and one is in small letters | VI1-T1647
55 | If the user edits document config which is already added in a work flow, the document config does not gets updated automatically | VI1-T1648
56 | User does not have any option to delete a single document config from workflow configuration | VI1-T1649
57 | Notification of the above senecio is wrong | VI1-T1650
58 | -Updated training module | VI1-T1651
59 | Remove workflow option while uploading documents for training | VI1-T1652
60 | Add a restriction on uploading documents in the normal flow if no document config is define | VI1-T1653
61 | Restrict user from uploading documents in normal flow if there are on document configurations which have completed training at least once | VI1-T1654
62 | Update the training classification to have a separate id for "Supporting documents" vs "New format" | VI1-T1655
63 | Training classification submission to have a warning/confirmation msg to convert all "New formats" to "SD" while submission | VI1-T1656
64 | Training classification should have an option to create a new doc config and update the new formats in the same iteration | VI1-T1657
65 | API-Remove workflow option while uploading documents for training and normal | VI1-T1668
66 | API change - Add a restriction on uploading documents in the normal flow if no document config is define | VI1-T1669
67 | API - Restrict user from uploading documents in normal flow if there are on document configurations which have completed training at least once | VI1-T1670
68 | API- Remove wokflow from all list api | VI1-T1671
69 | add ai api changes for training files | VI1-T1673
70 | Issue when the data is extracted for one doc and the users moves to second doc w/o saving doc one changes. | VI1-T1658
71 | If we rotate a file, it does not detect any parameter in the extraction | VI1-T1659
72 | -New table features | VI1-T1660
73 | Zoom on table | VI1-T1661
74 | Serial number on the image | VI1-T1662
75 | Column spacing in extraction view | VI1-T1663
76 | key board actions to move up/down/right/left | VI1-T1664
77 | tab to move to next field | VI1-T1665
78 | Dragging the contour from top left | VI1-T1666
79 | Scroll to contour | VI1-T1667
80 | Zoom level with 80%/90% | VI1-T1674
81 | Load testing on quadrant and add scalability features | VI1-T1672
82 | Lock feature not working w/o refresh of the page | VI1-T1675
83 | Getting unexpected error after doing full with and pressing tab two times | VI1-T1676
84 | In review classification, Invoice should not get an option of "Mark subsequent pages as invoice" | VI1-T1677
85 | Redirecting of the values is not happing from 1 page to another page | VI1-T1678
86 | During Zoom of the page if you add a table, there is an issue if you press edit the table. The contents are correctly extracted but the placement of the table is wrong | VI1-T1679
87 | Serial number on the values side is stuttering | VI1-T1680
88 | The Serial number on the table is too big and is covering the values | VI1-T1681
89 | When internet is slow the sniping API issue occurred | VI1-T1682
90 | Having issue in redirecting the data extracted by AI by clicking arrow keys | VI1-T1683
91 | After deletion of multiple files from batch, the deleted button is still visible | VI1-T1684
92 | If you delete any file that is in review completed, the same should get updated in Supervisor QC w/o any refresh | VI1-T1685
93 | After the user clicks on tabular data the platform should redirect the user to table directly | VI1-T1686
94 | In full width after extract data the table is getting disappeared | VI1-T1687
95 | UI issues for Full width | VI1-T1688
96 | Autofill countering is not visible in 1st attempt | VI1-T1689
97 | After selecting autofill feature and selecting the values, the serial number is coming undefined | VI1-T1690
98 | after click on reset button the full width should be close and minimise screen should be shown which functionality is not working | VI1-T1691
99 | Multiple page>> table delete >>minimise screen issue | VI1-T1692
100 | Cases: Table is extracted by AI >>after delete when user is click on the reset button the table thing should be automatically extended | VI1-T1693
101 | QC Screen & My document screen > Supervisor able to Delete the file. | VI1-T1694
102 | The Delete popup is not showing to the supervisor & indexer also when admin delete the same batches there supervisor have been working. | VI1-T1695
103 | supervisor have access to delete the files in classification reviewed and reviewed complete section on my document and QC screen. | VI1-T1696
104 | Feedback module UI testing on S3 Link | VI1-T1697
105 | New Workflow Tab Not Closing After 'Create' Button Click on Classification Review Screen | VI1-T1698
106 | Access is being granted to submit without defining the new format | VI1-T1699
107 | "Mark preceding pages as #NEW_FORMAT# " Functionality is converting document as a Invoice custom | VI1-T1700
108 | After deleting contouring in the PO date, the plus sign is not appearing to add contouring again. | VI1-T1701
109 | After placing contouring on the PO date, it is not automatically extracting the date. | VI1-T1702
110 | After you approve the OCR failed file, the batch that comes to API upload has a negative value in OCR successful | VI1-T1703
111 | After approve in OCR fail, a refresh is needed for the file to get populated in indexer screen | VI1-T1704
112 | The values I have detected automatically appear in the wrong place, and when I click on a cell, I can edit it right there. However, after clicking on the next cell it moves but we can not edit: Internal Stagging | VI1-T1705
113 | The cursor is not getting disabled once's focus is moved to a different cell. | VI1-T1706
114 | The image thumbnail shows correct however actual image shows tilled. | VI1-T1707
115 | Scroll issue | VI1-T1708
116 | Unable to submit the big file | VI1-T1709
117 | After clicking on the tab, the cell automatically shows an option for editing on Internal Stagging. | VI1-T1710
118 | When continuously clicking the up or down arrow, the scroll bar does not function as expected on Internal Stagging | VI1-T1711
119 | Special characters are not getting extracted | VI1-T1712
120 | Scroll issues when we click on the right-left arrows. | VI1-T1713
121 | Space issues in vendor address pincode | VI1-T1714
122 | Snippet issue case | VI1-T1715
123 | Date Format validation not working. | VI1-T1716
124 | Auto-column not working in this specific case | VI1-T1717
125 | Spacing issue in this specific case | VI1-T1718
126 | An error occurs when clicking on "Insert 1 row below" & "Insert 1 row above" | VI1-T1719
127 | Issue when the table is added while zoomed in and the user presses extract data | VI1-T1720
128 | After deleting of the table, if the user drags the contour, gettng an undefined error | VI1-T1721
129 | Once you add the contour and select a second value, the earlier contour is getting disappeared | VI1-T1722
130 | Payment Terms & Customer Name not showing up | VI1-T1723
131 | 100% file view is not on fit to screen ratio | VI1-T1724
132 | Issue in numeric field's validation | VI1-T1725
133 | Page error is happening | VI1-T1726
134 | Oriented feature is not applying in the thumbnail | VI1-T1727
135 | if you select autofill w/o giving any feedback, some of the values of the selected auto-fill column gets disappeared | VI1-T1728
136 | Update page range for table error | VI1-T1729
137 | If the user uses "-" symbol to enter date, the data is not getting validated. | VI1-T1730
138 | If you enter any wrong data and press enter, the validation text is not visible and the data disappears. | VI1-T1731
139 | If the user tries to select any drop down in Quantity, Unit Price, | VI1-T1732
140 | After inserting a row above or below, when I click on a blank box, the contouring box flips upside down. | VI1-T1733
141 | Numeric validation error for Amount | VI1-T1734
142 | If I select the 'Amount' option within the 'Unit Price,' AI is not capturing numbers after the comma (,) | VI1-T1735
143 | After force submit all the saved table is getting missed | VI1-T1736
144 | Submit is happening with validation errors | VI1-T1737
145 | When press a button to scroll up, the scroll gets stuck: Scalar | VI1-T1738
146 | The feature names are being cropped | VI1-T1739
147 | Ui Issue: Scaler | VI1-T1740
148 | After applying the validation the values are getting disappeared | VI1-T1741
149 | post clicking the cancel button on the force submit box it is roughing to the Header page. | VI1-T1742
150 | Classification Review>> Fit to screen not happening in the preview | VI1-T1743
151 | Vendor name / address and ID is not updated on review completed page after click on save progress button and Go back button | VI1-T1744
152 | Indexer changes is not showing on QC screen when supervisor change anything in the classification screen on Prod | VI1-T1745
153 | Partial work is done from admin and partial done from Indexer so during the QC the admin file should be appear locked but supervisor is able to do the work on admin file alsoOpen Details | VI1-T1746
154 | Default row Selection | VI1-T1427
155 | Table adjustment issue | VI1-T1428
156 | Table not detect properly | VI1-T1429
157 | After review complete user should be able to change anything in the table | VI1-T1431
158 | IF WE HAVE ONLY ONE PAGER DOCUMENT STILL SHOWING DELETE SECOND OPTION "Delete table on the entire document" | VI1-T1432
159 | Unable to create more than 2 row line | VI1-T1433
160 | Insert one row below feature is not working | VI1-T1434
161 | Unexpected screen error | VI1-T1435
162 | Relavent option not showing in the drop down | VI1-T1436
163 | Page Limitation Error | VI1-T1437
164 | Delete table on the current page Error | VI1-T1438
165 | Data not extracted | VI1-T1439
166 | Row overlapped issue | VI1-T1440
167 | After click on clear data "Countering error is showing" | VI1-T1441
168 | Not able to add table | VI1-T1442
169 | Unable to submit the review | VI1-T1443
170 | Unable to extract the value | VI1-T1444
171 | Unable to see table /delete or create | VI1-T1445
172 | Unable to create table | VI1-T1446
173 | Row per page showing incorrect count. | VI1-T1447
174 | -Countering having issues on a rotated file when we select any cells in a table. The page does not go to the concernned cell. | VI1-T1448
175 | Rotated file table issue | VI1-T1455
176 | Multiple pages of table, having issue of selecting dropdown. | VI1-T1449
177 | Delete button is not working | VI1-T1450
178 | If we directly click on "full width" table counting changes his place. | VI1-T1451
179 | When viewing the document at full width, only half of the document is visible. | VI1-T1452
180 | The dropdown option is displayed in the middle of the column | VI1-T1453
181 | Autofill column (dropdown) is not working | VI1-T1454
182 | After the review completed if the user is clicking tabular data, the images is getting disappeared. | VI1-T1457
183 | Unexpected Error if we switch between Keys Values and Tables values for a specific files. | VI1-T1458
184 | The countering issue is if we go back and forth between Keys and Values and Table Values. | VI1-T1459
185 | Unexpected Error if we click on table extraction section for the samples where AI has not detected the table. | VI1-T1460
186 | If you insert a column in a table and the change the dropdown. The values are automatically filled in the inserted colomn. | VI1-T1461
187 | Unable to extract the table showing error "All AI server down for auto table completion api" | VI1-T1462
188 | Autofill feature is not function on "Full Width" | VI1-T1463
189 | Auto-Column Feature not working consistently | VI1-T1464
190 | Auto-Column does not work when clicked on any other value of the table. | VI1-T1465
191 | Reset button should be functional when user will be change anything in the table | VI1-T1466
192 | The countering after insert of a column should be default countering | VI1-T1467
193 | Zoom in and Zoom out is not functional in full width and in normal review screen | VI1-T1468
194 | Once the user delete the rows of the table and selects a dropdown, the deleted row is not detected. | VI1-T1469
195 | If you extract the data from a table by making some changes, which has an invoice with 3 pages. 2nd page being an invoice or supporting document. The data is not coming on the second extraction. | VI1-T1470
196 | UI Issues : Please refer the screenshot | VI1-T1471
197 | UI Issue : Please refer the video | VI1-T1472
198 | Add table should not work for a supporting document inside an set of pages in an invoice | VI1-T1473
199 | When we modify a table the auto-complete rows does not appear, This feature is working on add table. | VI1-T1474
200 | The results from Round 4 are not matching with the results of the file getting converted from H to L | VI1-T1475
201 | "Tabular data" is outside of the table boundary. | VI1-T1476
202 | "Tabular Data" is not in the boundary. | VI1-T1477
203 | When changing vendors and clicking on "tabular data," the key and values within the tabular data box expand. | VI1-T1478
204 | The results from Round 4 are not matching with the results of the file getting converted from H to L [In Round 4 the table was capture but in current testing while converting from H to L, the table is not captured.] | VI1-T1479
205 | The table is not extracted. | VI1-T1480
206 | The column is missing after the 1st extraction | VI1-T1481
207 | Ui Issue | VI1-T1482
208 | Postment selective headers | VI1-T1483
209 | After add table row is not extracting automatically | VI1-T1484
210 | Reset Tabular Data button is not showing on full width | VI1-T1485
211 | Unable to create new table after delete | VI1-T1486
212 | Drop down option is not showing properly | VI1-T1487
213 | Page not navigating correctly on click of table cell | VI1-T1456
214 | Redirect of scroll after clicking on any values in table (Full width) | VI1-T1488
215 | Unable to see the preview and file thumbnail. | VI1-T1489
216 | The pre selected vendor does not have L in the vendor list dropdown in review files | VI1-T1490
217 | After adding an table, and extraction data. The auto rows are not getting captured | VI1-T1491
218 | By adding columns to the table the drop down is having issues. | VI1-T1492
219 | Reset functionality after deletion of the table, not functional for multiples pages. | VI1-T1493
220 | If we add table in multiple pages file and draw the table lines for page 1 and not for page 2, plus also extract data. The data is not captured by the AI | VI1-T1494
221 | If the user add table to multiple files and draws table for both. The AI only captured the table present in the second table and the Page 1 extracted data is blank. | VI1-T1495
222 | The countering in Autofill is not getting saved | VI1-T1496
223 | auto complete function not working once the user clicks on any value and then goes to dropdown to select auto-complete | VI1-T1497
224 | The user added column's to an existing table and extracted the data two times | VI1-T1498
225 | In multiple files use case, the reset button is causing to delete all files | VI1-T1499
226 | Extraction for multiple pages is not working for the samples where AI has failed to extract any table | VI1-T1500
227 | Extraction not functional on single page AI has failed to extract any table | VI1-T1501
228 | An extra line is getting created for the auto fill row feature | VI1-T1502
229 | Auto-Coloum not visible in the following scenario | VI1-T1504
230 | Snipet is not working | VI1-T1505
231 | Dropdown option after using auto-column feature is not giving proper results | VI1-T1506
232 | After extraction the table is not getting captured properly | VI1-T1507
233 | The data from the dropdown is visible after the counter is selected by the user | VI1-T1508
234 | After extract data the values are getting disappeared | VI1-T1509
235 | Ui Issue: The "Submit" button is not in alignment. | VI1-T1510
236 | In partial submit, feature like extract data is working | VI1-T1511
237 | In multiple pages invoices, the auto complete feature is not working for the 1st file. Also the rows are not getting saved for the first file | VI1-T1512
238 | Snippet is no functional after applying auto-complete feature | VI1-T1513
239 | After deleting the Table, Contouring box still remains on the screen | VI1-T1514
240 | User adding multiple pages in one invoice and then deleting the second page w/o extraction | VI1-T1515
241 | Countering feature is not functional after addition of row plus deletion of rows | VI1-T1516
242 | Counter is not working after making changes in the position of the snippet | VI1-T1517
243 | When zoomed in, the contouring box disappears from the extracted value. | VI1-T1518
244 | In multiple pages, the extract data should be available after selection of 2 rows for every page | VI1-T1519
245 | After deletion of the table of multipage after extraction. The extraction data bar still remains | VI1-T1520
246 | On Reviewed document screen, "How to Review a File?" process should not be appeared | VI1-T1521
247 | UI BUG on 90% Resolution | VI1-T1522
248 | If in an Invoice of 4 pages 1 page is rotated. The data for the 3 pages does not get extracted after adding the table in this invoice and extracting data. | VI1-T1523
249 | Tabular content error show | VI1-T1524
250 | If we add table to multiple pages and then delete a page table without extracting the data. Add items issue appears. | VI1-T1525
251 | Auto Columns : Disable the click of other columns when auto colums is applied | VI1-T1526
252 | In multiple pages if you delete every rows of 1 page. The add line item issue arrises | VI1-T1527
253 | If you click multiple times on "Add rows option" on the second item. Multiple rows will get created. | VI1-T1528
254 | Add line item after deleting the existing rows not working in "Full Width" | VI1-T1529
255 | If there is extraction happening for multiple pages, the headers in the dropdown are of the 2nd page. The headers should be of the 1st page | VI1-T1530
256 | The edited extracted rows are not getting extracted | VI1-T1531
257 | Dropdown options of the table are not appearing for QC screen for Supervisor. It appears only once the supervisor extracts the tables data once again. | VI1-T1532
258 | Auto row designed features is not working when user delete all the tables | VI1-T1533
259 | After clicking on "full width" the table Countering changes his place. | VI1-T1534
260 | After applying the autofill option contouring not showing. | VI1-T1535
261 | On full-width, When user trying to adjust or add a table, if user minimize the tab of tabular data, the user is unable to any type of changes in the table. | VI1-T1536
262 | Reprocessing is taking more then 2 min for a single page file | VI1-T1537
263 | Showing an incorrect button name. | VI1-T1538
264 | User after clicking to any value post that click on edit table. The table disappears | VI1-T1539
265 | Thumbnail getting blacked after rotation of the file. Change the status of the file to invoice [Rotated File] | VI1-T1540
266 | The image is breaking after these steps | VI1-T1541
267 | The headers of the table change after we do extract data | VI1-T1542
268 | Rotational features are working on the thumbnail but not working on the preview image. | VI1-T1543
269 | After making changes to the table for this file. Add line items issue | VI1-T1544
270 | The countering box is not changing after these steps | VI1-T1545
271 | Right side reset options is breaking the image | VI1-T1546
272 | AI in initial extraction giving different column's for same invoice pages | VI1-T1547
273 | Delete, Edit and Reset functionality not functional on the pages where there is no table | VI1-T1548
274 | Unable to see a preview of files | VI1-T1549
275 | If the user is doing extract data for rotated image in a multiple page invoice. The data gets disappeared for all the pages | VI1-T1550
276 | In multiple pages if we are adding a column to a invoice. Data is not getting extracted for the file, but we can extract the same going into a different file in same invoice. | VI1-T1551
277 | My documents > "Classification Reviewed > page needs to click on refresh, for file. | VI1-T1552
278 | Data getting disappeared after these steps | VI1-T1553
279 | If the user delete all the column's and add back them back. The same are not getting reflected on the consecutive pages | VI1-T1554
280 | Table headers are not getting for QC | VI1-T1555
281 | Image is getting disappeared | VI1-T1556
282 | Dropdown getting wrongly selected for multipage of QC extract | VI1-T1557
283 | After these following steps, delete table is not working | VI1-T1558
284 | Error coming in this file, after submitting batch | VI1-T1559
285 | "Add New Table" are displayed as negative numbers. | VI1-T1560
286 | In Add Table, If the user adds column's to one page the same is not applied to consecutive pages | VI1-T1561
287 | If we add a table in multiple pages and then delete the table on second page. The table column's on the 2st page gets deleted | VI1-T1562
288 | User able to add pages which are greater then the document pages | VI1-T1563
289 | Countering issue observed, after deleting the table. | VI1-T1564
290 | In multipage use case, if 2nd and 3rd page does not have headers in the table. The AI is still giving the headers for 2nd and 3rd page | VI1-T1565
291 | Extract data for 2nd page is resulting in bug in 1st page. | VI1-T1566
292 | Countering issue. | VI1-T1567
293 | Columns getting automatically added after extraction of the data | VI1-T1569
294 | UI Bug | VI1-T1570
295 | Issue in selecting the latest status of the vendor after applying best of 3 and best of 5 | VI1-T1571
296 | After adding a table, extract Data not working for a single page file | VI1-T1575
297 | In first extraction the AI is not catching the table properly | VI1-T1576
298 | Editing table issue | VI1-T1577
299 | Extract data not working for this specific file [Multipage File] | VI1-T1578
300 | Add line item issue on multiple page file | VI1-T1579
301 | Once you click on a dropdown in full width, the dropdown option does not disappear | VI1-T1580
302 | After extract data in multiple pages, data for some pages and the drop down are missing | VI1-T1581
303 | File total pages count is showing undefined [MARK STAGING] | VI1-T1582
304 | While scrolling in review files, the file is getting zoomed in | VI1-T1583
305 | Table glitch issue | VI1-T1584
306 | In review submitted, the value table are clickable | VI1-T1585
307 | The value on which autocoloum is applied is should wrong contour | VI1-T1586
308 | Table extraction not happening on the pages where the strategy has been changed from default > any other | VI1-T1587
309 | unable to submit a review on this batch Please refer to the Image | VI1-T1588
310 | Team Management : During creation of the supervisor, he should get the option to add him in multiple teams. | VI1-T1589
311 | Team Management : While selecting supervisors for Indexers during editing, An supervisor is shown belonging to only one team, but it should be shown the same supervisor that i pertaining to multiple teams. | VI1-T1590
312 | Only 1 team is showing under search option | VI1-T1591
313 | Facing the issue during the assigning process | VI1-T1592
314 | Error facing during the user editing | VI1-T1593
315 | The reassignment of teams from one supervisor to another is not working as expected. Supervisor XYZ remains in the default team instead of being moved to the former supervisor's teams | VI1-T1594
316 | The reassignment of teams from one supervisor to another is not working as expected. Supervisor XYZ remains in the default team instead of being moved to the former supervisor's teams | VI1-T1748
317 | The reassignment of teams from one supervisor to another is not working as expected. Supervisor XYZ remains in the default team instead of being moved to the former supervisor's teamsOpen Details | VI1-T1749
318 | After clicking multiple times on the "Extract Data" button row & column auto get deleted. | VI1-T1399
319 | Extraction Report : Additional Columns | VI1-T1406
320 | -Training Feature | VI1-T1407
321 | schema design | VI1-T1408
322 | create an api to upload training files | VI1-T1409
323 | create an API to listing of training batches | VI1-T1410
324 | create an API to listing of training documents | VI1-T1411
325 | Create an api for classification changes | VI1-T1412
326 | Send file to ai for ocr | VI1-T1413
327 | webhook to recieve ocr response | VI1-T1414
328 | send file to ai for KVP non rotated | VI1-T1415
329 | send file to ai for KVP rotated | VI1-T1416
330 | webhook to recieve kvp response | VI1-T1417
331 | send file to ai for rotate Images | VI1-T1418
332 | send file to ai for generate Pdf | VI1-T1419
333 | export traing data to ai | VI1-T1420
334 | Doc configuration | VI1-T1421
335 | Default Configuraton screen | VI1-T1422
336 | UI Issues: Prod | VI1-T1423
337 | Rotational features is working on the thumbnail but not working on the preview image: ProdOpen Details | VI1-T1424
338 | Vendor List : If a user edit the vendor in the vendor list and again edits the vendor as it was before edition. The red mark is still present in the vendor window. | VI1-T1425
339 | Vendor List : If the user gives best of 5 feedback to a file in which the vendor is already edited. The red mark is still present on the file with new vendor. | VI1-T1426